## Budget Overview
PROJECT BUDGET TRACKER
A live summary of the entries on the Expense Tracker sheet.
TOTAL PLANNED BUDGET |  | TOTAL ACTUAL SPENDING |  | REMAINING BUDGET |  | BUDGET VARIANCE
8000 |  | 6830 |  | 1170 |  | 1170
BUDGET STATUS | Under budget |  |  | SPEND VS. BUDGET | 85.38%
Remaining Budget = planned budget minus actual spending (the amount left; negative means overspent). Budget Variance = planned minus actual; positive means under budget, negative means over budget.
CATEGORY BREAKDOWN
Category variance = Planned minus Actual; positive means savings, negative means overspending.
Category | Planned | Actual | Variance
People | 1800 | 1500 | 300
Software | 900 | 900 | 0
Marketing | 2050 | 1450 | 600
Equipment | 1500 | 1250 | 250
Travel | 700 | 560 | 140
Operations | 450 | 450 | 0
Other | 600 | 720 | -120
TOTAL | 8000 | 6830 | 1170

## Expense Tracker
PROJECT BUDGET TRACKER
Blue cells are editable. Variance is Planned Cost minus Actual Cost: positive means under budget; negative means over budget.
Category | Item / Description | Planned Cost | Actual Cost | Variance | Due Date | Status | Notes
People | Freelance design | 1800 | 1500 | 300 | 2026-11-15 | Paid | Final invoice received
Software | Project management software | 900 | 900 | 0 | 2026-10-20 | Paid | Annual team plan
Marketing | Campaign creative assets | 1200 | 1450 | -250 | 2026-11-01 | In Progress | Example of an over-budget item
Equipment | Monitor and accessories | 1500 | 1250 | 250 | 2026-11-10 | Paid | Example equipment purchase
Travel | Client planning meeting | 700 | 560 | 140 | 2026-11-22 | Paid | Transport and one night
Operations | Domain and hosting | 450 | 450 | 0 | 2026-11-30 | Paid | Annual renewal
Marketing | Newsletter sponsorship | 850 |  |  | 2026-12-01 | Planned | Actual cost not entered yet
Other | Contingency printing | 600 | 720 | -120 | 2026-11-18 | In Progress | Example of a small overrun

## Instructions
HOW TO USE YOUR PROJECT BUDGET TRACKER
1. Start with the Expense Tracker | Replace the example entries with your own costs. Blue cells are for your input; the Variance column is calculated.
2. Use the dropdowns | Choose a Category and Status from the dropdowns. Edit the lists below if you need different options.
3. Enter amounts and dates | Enter planned and actual costs as numbers, and add due dates where useful. Leave Actual Cost blank until you know it.
4. Read the variance | Expense-row variance = Planned Cost minus Actual Cost. Positive means under budget (savings); negative means over budget.
5. Review the dashboard | Budget Variance = Planned Budget minus Actual Spending. Positive means under budget; negative means over budget. Remaining Budget is the planned amount left after actual spending; a negative amount means overspending.
6. Choose your currency | Amounts use AED by default. To change currency, select the amount cells and edit Number Format, replacing AED with your preferred currency code or symbol.
7. Add more expenses | Enter new expenses in the blank rows inside the table. The table filters and formulas are ready for the included input rows.
EDITABLE DROPDOWN LISTS
Categories | Statuses
People | Planned
Software | In Progress
Marketing | Paid
Equipment | On Hold
Travel | Cancelled
Operations
Other
Keep list entries together without blank rows so the dropdowns remain easy to use.